## Reference ID
Floor Code | Floor Name | Phase Code | Phase Name
SOG | slab on grade | SHU | Shuttering
1F | first floor | STF | Steelfixing
2F | second floor | POU | Pouring
3F | Third floor | DSH | Deshuttering
4F | fourth floor
5F | Fifth floor
PC | P.C
RC | R.C
GN | General

## Duration
Activity name | Production rate | Unit /day | Reference Duration
PC Founadtion shuttering | 10 | m2/day | 15
PC Founadtion Steelfixing | 2174 | kg/day | 20
PC Founadtion pouring | 23 | m3/day | 3
PC Founadtion Deshuttering | 20 | m2/day | 5
RC Founadtion Steelfixing | 2174 | kg/day | 10
RC Founadtion shuttering | 10 | m2/day | 7
RC Founadtion pouring | 34 | m3/day | 10
RC Founadtion Deshuttering | 14 | m2/day | 7
RC Column Steelfixing | 3847 | kg/day | 15
RC Column shuttering | 6 | m2/day | 20
RC Column pouring | 29 | m3/day | 14
RC Column Deshuttering | 12 | m2/day | 20
RC Slab Steelfixing | 1235 | kg/day | 10
RC Slab shuttering | 7 | m2/day | 7
RC Slab pouring | 24 | m3/day | 10
RC Slab Deshuttering | 10 | m2/day | 2

## Relationships
Pred Name | Rel Type | Succ Name | Lag
RC Column Formwork | FS | RC Column Steelfixing | 0
RC Column Steelfixing | FS | RC Column Casting | 0
RC Column Casting | FS | RC Column DeFormwork | 7
RC Slab Formwork | FS | RC Slab Steelfixing | 0
RC Slab Steelfixing | FS | RC Slab Casting | 0
RC Slab Casting | FS | RC Slab DeFormwork | 7
P.C - Foundation Steelfixing | FS | P.C - Foundation Formwork | 0
P.C - Foundation Formwork | FS | P.C - Foundation Casting | 0
P.C - Foundation Casting | FS | P.C - Foundation DeFormwork | 5
P.C - Foundation DeFormwork | FS | R.C - Foundation Formwork | 0
R.C - Foundation Formwork | FS | R.C - Foundation Steelfixing | 0
R.C - Foundation Steelfixing | FS | R.C - Foundation Casting | 0
R.C - Foundation Casting | FS | R.C - Foundation DeFormwork | 2